## Gantt Chart
	Asteroids				0%
	Third Element Aviation GmbH
	Birger Möllering		Sonntag, 26. April 2020

										18					19					20					21					22					23					24					25					26					27					28					29					30					31					32					33					34					35					36					37					38					39					40					41					42					43
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Apr-20				Mai-20					Jun-20					Jul-20					Aug-20					Sep-20					Okt-20
			27.04.20	7	27.04.20	0%	7			27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24
	Ressourcen Evaluation		27.04.20	1	27.04.20	0%	0	0	0
	Ressourcen auflisten		27.04.20	0,17	27.04.20
	Grafiken		27.04.20	0,17	27.04.20
	Bibliotheken		27.04.20	0,17	27.04.20
	Werkzeuge auflisten		27.04.20	0,17	27.04.20
	Planungswerkzeuge		27.04.20	0,17	27.04.20
	Implementationswerkzeuge		27.04.20	0,17	27.04.20
	Milestone 1	Ressourcenplan	27.04.20	1	27.04.20

	Programmplanung		28.04.20	1	28.04.20		0	0	0
	Komponentenrelationen visualisieren		28.04.20	1	28.04.20
	Milestone 2	Diagramm	28.04.20	1	28.04.20

	Implementation		29.04.20	2	30.04.20		0	0	0
	Komponenten implementieren		29.04.20	1	29.04.20
	Komponenten verknüpfen		30.04.20	1	30.04.20
	Milestone 3	Asteroids	30.04.20	2	30.04.20

	Präsentation		01.05.20	1	01.05.20		0	0	0
	Datum vereinbaren		01.05.20	0,5	01.05.20
	Powerpoint slides erstellen o.ä.		01.05.20	0,5	01.05.20
	Milestone 3	Präsentation

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		01.01.14
		04.03.14
		18.04.14
		20.04.14
		25.04.14
		01.05.14
		10.06.14
		15.08.14
		08.12.14
		25.12.14