## Gantt Chart
| Asteroids |  |  |  | 0%
Third Element Aviation GmbH
| Birger Möllering |  | 2020-04-26
[10 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43
WBS | Task Names | Resource Names | Start | Duration | Finish | % Complete | Calendar days | Days Completed | Days Remaining | 2020-04-27 |  |  |  | 2020-05-01 | [30 empty] | 2020-06-01 | [29 empty] | 2020-07-01 | [30 empty] | 2020-08-01 | [30 empty] | 2020-09-01 | [29 empty] | 2020-10-01
|  |  | 2020-04-27 | 7 | 2020-04-27 | 0% | 7 | time axis 2020-04-27 to 2020-10-24
| Ressourcen Evaluation |  | 2020-04-27 | 1 | 2020-04-27 | 0% | 0 | 0 | 0 | bar: 2020-04-27 to 2020-06-07
| Ressourcen auflisten |  | 2020-04-27 | 0.16667 | 2020-04-27
| Grafiken |  | 2020-04-27 | 0.16667 | 2020-04-27
| Bibliotheken |  | 2020-04-27 | 0.16667 | 2020-04-27
| Werkzeuge auflisten |  | 2020-04-27 | 0.16667 | 2020-04-27
| Planungswerkzeuge |  | 2020-04-27 | 0.16667 | 2020-04-27
| Implementationswerkzeuge |  | 2020-04-27 | 0.16667 | 2020-04-27
| Milestone 1 | Ressourcenplan | 2020-04-27 | 1 | 2020-04-27
| Programmplanung |  | 2020-04-28 | 1 | 2020-04-28 |  | 0 | 0 | 0 | bar: 2020-04-27 to 2020-06-07
| Komponentenrelationen visualisieren |  | 2020-04-28 | 1 | 2020-04-28
| Milestone 2 | Diagramm | 2020-04-28 | 1 | 2020-04-28
| Implementation |  | 2020-04-29 | 2 | 2020-04-30 |  | 0 | 0 | 0
| Komponenten implementieren |  | 2020-04-29 | 1 | 2020-04-29
| Komponenten verknüpfen |  | 2020-04-30 | 1 | 2020-04-30
| Milestone 3 | Asteroids | 2020-04-30 | 2 | 2020-04-30
| Präsentation |  | 2020-05-01 | 1 | 2020-05-01 |  | 0 | 0 | 0
| Datum vereinbaren |  | 2020-05-01 | 0.5 | 2020-05-01
| Powerpoint slides erstellen o.ä. |  | 2020-05-01 | 0.5 | 2020-05-01
| Milestone 3 | Präsentation
Gantt Chart Template V1.1
Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>
How To Use
INSERT LINES:
Insert the required number of lines: click the line number and drag down
From the template, copy the required section or just one line
INPUT DATA:
WBS: to itemize the WBS copy and past the required level from the template
Enter a Task and Resource Names
Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.
Holidays
2014-01-01
2014-03-04
2014-04-18
2014-04-20
2014-04-25
2014-05-01
2014-06-10
2014-08-15
2014-12-08
2014-12-25